## Status Report
TEST SCENARIOS & CONDITIONS
[Project Name] : Test Summary Report
Module/s | Work Items | Resource | Start Date | Finish Date | Total # of ProdCode per Scenario | Passed | Failed | In Progress | Descoped | Deferred | Not Started | Execution Rate | Pass Rate | Status | Defect Reference No. | Severity | dd/mm <Resource Initial>: Comment/s
| EMA-TC0001 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0002 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0003 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0004 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0005 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0006 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0007 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0008 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0009 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0010 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0011 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0012 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0013 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0014 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0015 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0016 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0017 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0018 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0019 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0020 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0021 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0022 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0023 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0024 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0025 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0026 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0027 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0028 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0029 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0030 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0031 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0032 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0033 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0034 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0035 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0036 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0037 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0038 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0039 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0040 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0041 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0042 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0043 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0044 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0045 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0046 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0047 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0048 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0049 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0050 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0051 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0052 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0053 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0054 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0055 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0056 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0057 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0058 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0059 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0060 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0061 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0062 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0063 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0064 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0065 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0066 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0067 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0068 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0069 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0070 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0071 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0072 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0073 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0074 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0075 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0076 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 2 | -100% | 0% | N/A | 0 | 0 | 0
| EMA-TC0077 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0078 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
| EMA-TC0079 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 33.33% | 33.33% | Passed | 0 | 0 | 0
TOTAL |  |  |  |  | 237 | 46 | 0 | 0 | 33 | 0 | 158 | 19.41% | -3281%
Formulas:
Finish Date = [Start Date]

## Functional
BASIC INFO:
Project
Test Stage | QA Testing
Work Stream
Description:
Number of Test Conditions
[6 empty] | Test Preparation |  |  |  | Test Execution |  |  | Resource [QA Tester] | Date Tested (dd/mm/yyyy) | Defect Reference No. [AIL Number] | Severity | Comments [Comments/Suggestions/Error Description]
[6 empty] | User Type | Browser Type |  |  | Browser Type
Module | Test Condition ID | Test Condition | Test Steps | Expected Result | Test Data | Participant | Google Chrome | Mozilla Firefox | Internet Explorer | Google Chrome | Mozilla Firefox | Internet Explorer
Participant's Dashboard | EMA-TC0001 | Verify that page will redirected to Participant's Dashboard Page upon clicking again the Emailed Link, if Participant's Survey is still In-progress | 1. Click Emailed Link from Registration Approval Email | Page is redirecteded to Participant's Dashboard Page |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0002 | Verify that page will redirected to EMA Website upon clicking the EMA Logo | 1. Click Emailed Link from Registration Approval Email 2. Click EMA Logo | Page is redirecteded to EMA Website |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0003 | Verify that page will redirected to OSEA Website upon clicking the OSEA Logo | 1. Click Emailed Link from Registration Approval Email 2. Click OSEA Logo | Page is redirecteded to OSEA Website |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0004 | Verify that page will redirected to CECC Website upon clicking the CECC Logo | 1. Click Emailed Link from Registration Approval Email 2. Click CECC Logo | Page is redirecteded to CECC Website |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0005 | Verify that page will redirected to Business Central Website upon clicking the Business Central Logo | 1. Click Emailed Link from Registration Approval Email 2. Click Business Central Logo | Page is redirecteded to Business Central Website |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0006 | Verify that page will redirected to Company Information Page upon clicking the Company Info Tab | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab | Page is redirecteded to Company Information Page |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0007 | Verfiy that page will redirected to Survey Page upon clicking the Survey Tab | 1. Click Emailed Link from Registration Approval Email 2. Click Survey Tab | Page is redirecteded to Survet Page |  | Y | Y | Y | Y | Passed | Not Started | Not Started
Company Information Page | EMA-TC0008 | Verify that the following Panel is available upon page load : - Industry Sector - Private or Public Sector - Not-for-Profit - Revenue - Number of Employees - 90 Day Trial Periods - Sick Leave - Annual Leave - Business Outlook - Wage & Salary Reviews | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab | The following Panel is available upon page load : - Industry Sector - Private or Public Sector - Not-for-Profit - Revenue - Number of Employees - 90 Day Trial Periods - Sick Leave - Annual Leave - Business Outlook - Wage & Salary Reviews |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0009 | Verify that Company Information is dislplayed upon page load | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab | The Company Information is dislplayed upon page load |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0010 | Verify that Industry Sector is required | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Industry Sector Panel | Industry Sector is required |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0011 | Verify that page will redirected to Industry Selection Page upon clicking the Select and Industry Link | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Industry Sector Panel 4. Click Select an Industry Link | Page is redirected to Industry Selection Page upon clicking the Select and Industry Link |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0012 | Verify that Organization Sector Dowpdown List contains the following option: - Private - Public - Local Government | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Private or Public Sector Panel | Organization Sector Dowpdown List contains the following option: - Private - Public - Local Government |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0013 | Verify that Private or Public Sector is required | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Private or Public Sector Panel 4. Select Blank Option 5. Click Save Button | Private or Public Sector is required |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0014 | Verify that error message "Private or Public Sector is required" is displayed upon clicking the Save Button, if there's no selected Private pr Public Sector |  | The error message "Private pr Public Sector is required" is displayed upon clicking the Save Button, if there's no selected Private pr Public Sector |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0015 | Verify that the radio button under Not-for-Profit Panel is clickable | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Not-for-Profit Panel 4. Click Radio Button | The radio button under Not-for-Profit Panel is clickable |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0016 | Verify that Not-for-Profit is required | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Not-for-Profit Panel 4. Remove selected Not-for-Profit answer | Not-for-Profit is required |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0017 | Verify that error message "Not for Profit is required" is displayed upon clicking the Save Button, if there's no selected answer for Not-for-Profit Question |  | The error message "Not for Profit is required" is displayed upon clicking the Save Button, if there's no selected answer for Not-for-Profit Question |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0018 | Verify that Revenue Dowpdown List contains the following option: - Less than 1 million - 1 Million to less than 5 Million - 5 Million to less than 10 Million - 10 Million to less than 15 Million - 15 Million to less than 20 Million - 20 Million to less than 30 Million - 30 Million to less than 50 Million - 50 Million to less than 100 Million - 100 Million to less than 500 Million - Over 500 Million | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Revenue Panel 4. Click Dropdown List | Revenue Dowpdown List contains the following option: - Less than 1 million - 1 Million to less than 5 Million - 5 Million to less than 10 Million - 10 Million to less than 15 Million - 15 Million to less than 20 Million - 20 Million to less than 30 Million - 30 Million to less than 50 Million - 50 Million to less than 100 Million - 100 Million to less than 500 Million - Over 500 Million |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0019 | Verify that Revenue is required | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Revenue Panel 4. Select Blank Option 5. Click Save Button | Revenue is required |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0020 | Verify that error message "Revenue is required" is displayed upload click the Save Button, if there's no selected Revenue |  | The error message "Revenue is required" is displayed upload click the Save Button, if there's no selected Revenue |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0021 | Verify that Number of Employees is required | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Number of Employees Panel 4. Delete existing information 5. Click Save Button | Number of Employees is required |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0022 | Verify that error message "Number of Employees is required" is displayed upon clicking the Save Button, if Number of Employees is blank/empty |  | The error message "Number of Employees is required" is displayed upon clicking the Save Button, if Number of Employees is blank/empty |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0023 | Verify that Number of Employees field only accepts Numeric Character | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Number of Employees Panel 4. Input Latin or Special Characters | Number of Employees field only accepts Numeric Character |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0024 | Verify that Number of Employees field only accepts Maximum of 6 Characters | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Number of Employees Panel 4. Input more than 6 Characters | Number of Employees field only accepts Maximum of 6 Characters |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0025 | Verify that the radio button under 90 Day Trial Periods Panel is clickable | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to 90 Day Trial Periods Panel 4. Click Radio Button | The radio button under 90 Day Trial Periods Panel is clickable |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0026 | Verify that 90 Day Trial Periods is required | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to 90 Day Trial Periods Panel 4. Remove selected answer for 90 Day Trial Periods | 90 Day Trial Periods is required |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0027 | Verify that error message "Trial Period is required" is displayed upon clicking the Save Button, if there's no selected answer for 90 Day Trial Periods |  | The error message "Trial Period is required" is displayed upon clicking the Save Button, if there's no selected answer for 90 Day Trial Periods |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0028 | Verify that What is the highest number of sick days taken by any one employee? field only accepts Numeric Character | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Sick Leave Panel 4. Input Latin or Special Characters | What is the highest number of sick days taken by any one employee? field only accepts Numeric Character |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0029 | Verify that What is the highest number of sick days taken by any one employee? field only accepts Maximum of 5 Characters | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Sick Leave Panel 4. Input more than 6 Characters | What is the highest number of sick days taken by any one employee? field only accepts Maximum of 5 Characters |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0030 | Verify that What is the average number of sick days taken by all employees? field only accepts Numeric Character | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Sick Leave Panel 4. Input Latin or Special Characters | What is the average number of sick days taken by all employees? field only accepts Numeric Character |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0031 | Verify that What is the average number of sick days taken by all employees? field only accepts Maximum of 5 Characters | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Sick Leave Panel 4. Input more than 6 Characters | What is the average number of sick days taken by all employees? field only accepts Maximum of 5 Characters |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0032 | Verify that What is the highest number of annual leave days accumulated by any one employee? field only accepts Numeric Character | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Annual Leave Panel 4. Input Latin or Special Characters | What is the highest number of annual leave days accumulated by any one employee? field only accepts Numeric Character |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0033 | Verify that What is the highest number of annual leave days accumulated by any one employee? field only accepts Maximum of 5 Characters | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Annual Leave Panel 4. Input more than 6 Characters | What is the highest number of annual leave days accumulated by any one employee? field only accepts Maximum of 5 Characters |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0034 | Verify that What is the average number of annual leave days accumulated by all employees? field only accepts Numeric Character | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Annual Leave Panel 4. Input Latin or Special Characters | What is the average number of annual leave days accumulated by all employees? field only accepts Numeric Character |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0035 | Verify that What is the average number of annual leave days accumulated by all employees? field only accepts Maximum of 5 Characters | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Annual Leave Panel 4. Input more than 6 Characters | What is the average number of annual leave days accumulated by all employees? field only accepts Maximum of 5 Characters |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0036 | Verify that the radio button under What is your organisation’s overall outlook for business conditions in the next 12 months? is clickable | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Business Outlook Panel 4. Click Radio Button | The radio button under What is your organisation’s overall outlook for business conditions in the next 12 months? is clickable |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0037 | Verify that the radio button under What are your organisation’s expectations regarding employee numbers in the next 12 months? is clickable | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Business Outlook Panel 4. Click Radio Button | The radio button under What are your organisation’s expectations regarding employee numbers in the next 12 months? is clickable |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0038 | Verify that What was your organisation's average percentage increase during the last 12 months? field only accepts Numeric Character | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Wage & Salary Reviews Panel 4. Input Latin or Special Characters | What was your organisation's average percentage increase during the last 12 months? field only accepts Numeric Character |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0039 | Verify that What was your organisation's average percentage increase during the last 12 months? field only accepts Maximum of 5 Characters | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Wage & Salary Reviews Panel 4. Input more than 6 Characters | What was your organisation's average percentage increase during the last 12 months? field only accepts Maximum of 5 Characters |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0040 | Verify that What is your organisation's budgeted average percentage increase for the next 12 months? field only accepts Numeric Character | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Wage & Salary Reviews Panel 4. Input Latin or Special Characters | What is your organisation's budgeted average percentage increase for the next 12 months? field only accepts Numeric Character |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0041 | Verify that What is your organisation's budgeted average percentage increase for the next 12 months? field only accepts Maximum of 5 Characters | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Wage & Salary Reviews Panel 4. Input more than 6 Characters | What is your organisation's budgeted average percentage increase for the next 12 months? field only accepts Maximum of 5 Characters |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0042 | Verify that radio button under When does your organisation review wages and salaries (for the majority of employees)? Is clickable | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Wage & Salary Reviews Panel 4. Click Radio Button | The radio button under When does your organisation review wages and salaries (for the majority of employees)? Is clickable |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0043 | Verify that Month Dropdown list is displayed, if "A specific month each year - please specify" Radion Button is selected under When does your organisation review wages and salaries (for the majority of employees)? Question | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Go to Wage & Salary Reviews Panel 4. Select "A specific month each year - please specify" Radio Button | Month Dropdown list is displayed, if "A specific month each year - please specify" Radion Button is selected under When does your organisation review wages and salaries (for the majority of employees)? Question |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0044 | Verify that All Modifications will be saved upon clicking the Save Button, if all required fields are valid | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Modify Company Information 4. Click Save Button | All Modifications will be saved upon clicking the Save Button, if all required fields are valid |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0045 | Verify that page will be redirected to Survey Page upon clicking the Save Button, if all required fields are valid |  | Page will be redirected to Survey Page upon clicking the Save Button, if all required fields are valid |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0046 | Verify that page will redirected to Company Information Print Preview upon clicking the Print Button | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Click Print Button | Page will redirected to Company Information Print Preview upon clicking the Print Button |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0047 | Verify that Print Window will be displayed upon clicking the Print Button | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Click Print Button 4. Click Print Button | Print Window will be displayed upon clicking the Print Button |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0048 | Verify that Company Information Print Preview will be closed upon clicking the Close Button | 1. Click Emailed Link from Registration Approval Email 2. Click Company Info Tab 3. Click Print Button 4. Click Close Button | Company Information Print Preview will be closed upon clicking the Close Button |  | Y | Y | Y | Y | Passed | Not Started | Not Started
Survey Page | EMA-TC0049 | Verify that the following Panel/Element is available upon page load : - Survey Table - Add Postion Button - Survey Completed Button - Save a copy Button - Refresh Button | 1. Click Emailed Link from Registration Approval Email | The following Panel/Element is available upon page load : - Survey Table - Add Postion Button - Survey Completed Button - Save a copy Button - Refresh Button |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0050 | Verify that Survey Table displays the list of survey taken by the Participant | 1. Click Emailed Link from Registration Approval Email | Survey Table displays the list of survey taken by the Participant |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0051 | Verify that page will redirected to Positional Data Print Preview upon clicking the Print Link | 1. Click Emailed Link from Registration Approval Email 2. Click Prink Link | Page will redirected to Positional Data Print Preview upon clicking the Print Link |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0052 | Verify that Print Window will be displayed upon clicking the Print Button | 1. Click Emailed Link from Registration Approval Email 2. Click Prink Link 3. Click Print Button | Print Window will be displayed upon clicking the Print Button |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0053 | Verify that Positional Data Print Preview will be closed upon clicking the Close Button | 1. Click Emailed Link from Registration Approval Email 2. Click Prink Link 3. Click Close Button | Positional Data Print Preview will be closed upon clicking the Close Button |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0054 | Verify that Survey Information is displayed upon clicking the Arrow Icon of the Survey | 1. Click Emailed Link from Registration Approval Email 2. Click Arrow Icon | Survey Information is displayed upon clicking the Arrow Icon of the Survey |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0055 | Verify that page will be redirected to Question 1 to 4 Edit Page upon clicking the Edit Link beside Question 1 | 1. Click Emailed Link from Registration Approval Email 2. Click Arrow Icon 3. Click Edit Link | Page will be redirected to Question 1 to 4 Edit Page upon clicking the Edit Link beside Question 1 |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0056 | Verify that page will be redirected to Question 5 Edit Page upon clicking the Edit Link beside Question 5 | 1. Click Emailed Link from Registration Approval Email 2. Click Arrow Icon 3. Click Edit Link | Page will be redirected to Question 5 Edit Page upon clicking the Edit Link beside Question 5 |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0057 | Verify that page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 6 | 1. Click Emailed Link from Registration Approval Email 2. Click Arrow Icon 3. Click Edit Link | Page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 6 |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0058 | Verify that page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 7 | 1. Click Emailed Link from Registration Approval Email 2. Click Arrow Icon 3. Click Edit Link | Page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 7 |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0059 | Verify that page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 8 | 1. Click Emailed Link from Registration Approval Email 2. Click Arrow Icon 3. Click Edit Link | Page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 8 |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0060 | Verify that page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 9 | 1. Click Emailed Link from Registration Approval Email 2. Click Arrow Icon 3. Click Edit Link | Page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 9 |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0061 | Verify that page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 10 | 1. Click Emailed Link from Registration Approval Email 2. Click Arrow Icon 3. Click Edit Link | Page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 10 |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0062 | Verify that page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 11 | 1. Click Emailed Link from Registration Approval Email 2. Click Arrow Icon 3. Click Edit Link | Page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 11 |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0063 | Verify that page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 12 | 1. Click Emailed Link from Registration Approval Email 2. Click Arrow Icon 3. Click Edit Link | Page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 12 |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0064 | Verify that page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 13 | 1. Click Emailed Link from Registration Approval Email 2. Click Arrow Icon 3. Click Edit Link | Page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 13 |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0065 | Verify that page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 14 | 1. Click Emailed Link from Registration Approval Email 2. Click Arrow Icon 3. Click Edit Link | Page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 14 |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0066 | Verify that page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 15 | 1. Click Emailed Link from Registration Approval Email 2. Click Arrow Icon 3. Click Edit Link | Page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 15 |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0067 | Verify that page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 16 | 1. Click Emailed Link from Registration Approval Email 2. Click Arrow Icon 3. Click Edit Link | Page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 16 |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0068 | Verify that page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 17 | 1. Click Emailed Link from Registration Approval Email 2. Click Arrow Icon 3. Click Edit Link | Page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 17 |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0069 | Verify that page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 18 | 1. Click Emailed Link from Registration Approval Email 2. Click Arrow Icon 3. Click Edit Link | Page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 18 |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0070 | Verify that page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 19 | 1. Click Emailed Link from Registration Approval Email 2. Click Arrow Icon 3. Click Edit Link | Page will be redirected to Question 6 Edit Page upon clicking the Edit Link beside Question 19 |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0071 | Verify that Survey Table will be refreshed upon clicking the Refresh Button | 1. Click Emailed Link from Registration Approval Email 2. Click Refresh Button | Survey Table will be refreshed upon clicking the Refresh Button |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0072 | Verify that Survey Table will be saved/extracted as Excel File upon clicking the Save a copy Button | 1. Click Emailed Link from Registration Approval Email 2. Click Save a copy Button | Survey Table will be saved/extracted as Excel File upon clicking the Save a copy Button |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0073 | Verify that page will redirected to Positional Survey upon clicking the Add Position Button | 1. Click Emailed Link from Registration Approval Email 2. Click Add Position Button | Page will redirected to Positional Survey upon clicking the Add Position Button |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0074 | Verify that Survey Completed Button is disabled, if there's an On-going Survey | 1. Click Emailed Link from Registration Approval Email 2. Click Survey Completed Button | Survey Completed Button is disabled, if there's an On-going Survey |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0075 | Verify that validation message "WARNING: By clicking this button, you are indicating that you have completed entering data and the link will be disabled" is displayed upon clicking the Survey Completed Button, if all survey is Completed | 1. Click Emailed Link from Registration Approval Email 2. Complete all Survey 3. Click Survey Completed Button | The validation message "WARNING: By clicking this button, you are indicating that you have completed entering data and the link will be disabled" is displayed upon clicking the Survey Completed Button, if all survey is Completed |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0076 | Verify that validation message "WARNING: By clicking this button, you are indicating that you have completed entering data and the link will be disabled" will be closed upon clickng the Cancel Button | 1. Click Emailed Link from Registration Approval Email 2. Complete all Survey 3. Click Survey Completed Button 4. Click Cancel Button | The validation message "WARNING: By clicking this button, you are indicating that you have completed entering data and the link will be disabled" will be closed upon clickng the Cancel Button |  | Y | Y | Y | Y | Descoped | Not Started | Not Started
| EMA-TC0077 | Verify that page will be redirected to Thank you Page upon clicking the OK Button in validation message "WARNING: By clicking this button, you are indicating that you have completed entering data and the link will be disabled" | 1. Click Emailed Link from Registration Approval Email 2. Complete all Survey 3. Click Survey Completed Button 4. Click OK Button | Page will be redirected to Thank you Page upon clicking the OK Button in validation message "WARNING: By clicking this button, you are indicating that you have completed entering data and the link will be disabled" |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0078 | Verfiy that Survey Link will be disabled upon Completion of the Survey | 1. Click Emailed Link from Registration Approval Email 2. Complete all Survey 3. Click Survey Completed Button 4. Click OK Button 5. Click Emailed Link from Registration Approval Email | Survey Link will be disabled upon Completion of the Survey |  | Y | Y | Y | Y | Passed | Not Started | Not Started
| EMA-TC0079 | Verify that page will be redirected to Survey Closed Page upon clicking the Survey Link, if Survey is already Completed |  | Page will be redirected to Survey Closed Page upon clicking the Survey Link, if Survey is already Completed |  | Y | Y | Y | Y | Passed | Not Started | Not Started

## Out of Scope
Verify that Industry Sector is required

## Error Summary
Project:
Date:
Time:
Test Details:
Data List
RESULT | SEVERITY | PRIORITY | Browser
Pass | Blocker | Resolve Immediately | All Browser
Fail | Major | Give High Attention | Google Chrome
| Minor | Normal Queue | Internet Explorer
| Nice To Have | Defer | Mozilla Firefox
Safari (Mac)
Module:
Tester:
Remarks: | Cycle 1
Item Number | Module | Steps to Recreate Issue | Expected Result | Actual Result | Broswer | Severity | Priority | Reference #

## Defect Sev&Prio Definitions
Defect Severity Definition
Blocker
- Memory leak
- Main function cannot work and testing is at a dead-end
- Conflict with Software Application and Hardware
- Consistent crash during processing of a particular type of application, a user could not complete that type of application
- Incorrect data is passed resulting in corruption or system crashes
- Business Logic error that causes the system to hang
- Incorrect DLL/Program version installed
- Data or Database Problem
Major – Major defects are severe system outage causing a major function to periodically fail. Failures of major functions with “practical” work around or recovery possible are also included in this category. Examples are:
- Functionality does not work under certain conditions
- System Performance noticeably slows down
- Functionality works but not all parts of the function can be executed properly
- Generated reports contain inaccurate or erroneous values
- Missing or incorrect data validation
- Usability issues
- Requirements defect
- Data is affected with medium impact
- There is an alternative method of completing a particular process
Minor – Minor defects pertain to minor functions not working properly or are non-disruptive errors. Though such defects may be insignificant, too many minor faults may affect the system’s overall quality. Examples are:
- Minor display / redraw problem
- Inconvenience to user but does not happen frequently
- Poorly worded texts (e.g. incorrect grammar, etc.)
- Minor design or presentation issues (e.g. short-cut keys, enabled/disabled buttons)
- Misspelled words
- Documentation
- Incorrect or no help text on screens
- Dropdown list repeats or misses an option
- Cosmetic Errors
Nice to Have – Nice-to-haves are enhancements with no effect on the quality but may appear as proposals in order to enhance the system.
Defect Priority Definition
Resolve Immediately - Further development and/or testing cannot occur until the defect has been repaired. The system cannot be used until the repair has been effected.
Give High Attention - The defect must be resolved as soon as possible because it is impairing development/and or testing activities. System use will be severely affected until the defect is fixed.
Normal Queue - The defect should be resolved in the normal course of development activities. It can wait until a new build or version is created.
Defer - The defect repair can be put of indefinitely. It can be resolved in a future major system revision or not resolved at all.